## Slide 1: From Methodology to Execution Digital Project Management

## Slide 2: Project Scenario Digital Project Management

## Slide 3: Overview
You are a project manager for Yosemite, an eCommerce company that integrates brick-and-mortar stores onto its platform for a fee. You have been assigned to work with The Stefano Shop, a family-run business that had been a local success but was struggling to stay open. The primary business goal is to digitize the store’s operations and sales and complete this project in a maximum of 12 weeks.
Integrating The Stefano Shop into Yosemite means building the following features:
A storefront on the platform,
A social media integration, and
A recommendation engine.
The Stefano family, which consists of Papa Stefano, Mama Stefano, and Junior Stefano, will also require the training and knowledge to operate their digital store once it has been developed.

## Slide 4: Project Budget
The Yosemite storefront, training, and documentation can be delivered for $15,000 - a tight budget for the Stefanos. So Papa Stefano asked that you include a cost-benefit analysis in the project scope to reassure him this is a good investment.
For the cost-benefit analysis, your research shows:
The eCommerce industry discount rate is 20%
Yosemite promises a $36,000 increase in revenue
The cost of the project is $15,000

## Slide 5: Yosemite teams and tasks
Aliyah - Engineering Manager
Tasks:
Build storefront
Build social media integration
Build recommendation engine.
Each task takes two weeks of work.
Each task involves design, build, test, and release.
Moe - Vendor Manager
Tasks:
Inputting all inventory data after the storefront is delivered. It takes one week to add the inventory data.
Onboarding and training Stefano's before the store goes live. It takes one week to train them.
Create a custom sales report that is automatically sent to Stefanos during or after the recommendation engine is released. It takes one week to set up the reporting.
Taylor - Marketing Manager
Tasks:
Creating social media channels and handing them off to Stefano's. It takes a week, but this task must occur before the social media integration by the Engineering team.

## Slide 6: The Stefano Family
Papa Stefano has a strong presence in the family business but listens to Mama Stefano when making business decisions. He manages the floor and is averse to new technology. While he understands it’s time to modernize the shopping experience and wants to gain new customers, he’s wary of going over budget.
Mama Stefano keeps spreadsheets to track inventory and has convinced Papa to work with Yosemite. Her primary focus is on back-end administrative tasks of the business. Mama is more concerned about preparing the store for Christmas shoppers in time.
Junior Stefano is a high school student still learning about the family business. Junior creates social media posts on her own accounts for the store. Sees value in taking full advantage of Yosemite’s services.

## Slide 7: Yosemite team
Moe is the Yosemite Vendor Manager; he tends to be enthusiastic about upselling customers with additional services, not mindful of budget. Moe primarily focuses on promoting and coordinating Yosemite's services, which is part of the overall project. Additionally, this project is one of many he works on.
Aliyah is the Yosemite Engineering Manager, experienced and skilled. She prefers to work in Agile sprints but understands that not all customers can keep up with that pace. Her expertise in developing and implementing technical solutions enables her to guide the project's timeline and execution strategy, making her vital in determining the project's overall direction and progress.
Taylor, the Yosemite Marketing Manager, tends to take on too many assignments and can delay completing tasks. Taylor often needs to be informed of their assignments ahead of time. His role and contributions are limited to supporting the implementation of this project's marketing plans.
Lou is the Yosemite Small Business Program Manager and oversees all accounts under the Small Business category. You report directly to Lou. Lou only keeps a high-level overview of this project and its progress. He wants to showcase your project to the entire company if all goes well and expect regular communication, especially when things go wrong.

## Slide 8: Step One: Project Scope Digital Project Management

## Slide 9: Objectives, milestones, and resources
Describe the business objectives of the project in 1-2 sentences
The primary objective of the project is to digitalise the family-run shop called “The Stefano Shop” and improve its operations and sales, by integrating it into Yosemite's eCommerce platform. The online store aims to modernise the shopping experience, attract new customers, and streamline back-end administrative tasks while adhering to budget constraints and ensuring timely completion to prepare for the holiday season.
List at least 3 project milestones
Completion of the storefront development on the Yosemite platform, ensuring a digital presence for The Stefano Shop. Integration of social media channels with the storefront, providing successful promotion and engagement with customers across multiple platforms. Implementing the recommendation engine, which will improve the shopping experience by providing personalised product recommendations to customers based on their preferences and browsing history.
List the resources you have access to as the project manager, including the budget
Yosemite's Engineering Team (Led by Aliyah): Who is responsible for building the storefront, social media integration, and recommendation engine. The team has expertise in technical solutions and implementation. Yosemite's Marketing Team (Led by Taylor): Is tasked with creating and managing social media channels and marketing strategies. They are proficient in promoting and coordinating marketing. Yosemite's Vendor Management Team (Led by Moe): They can assist with coordinating additional services and resources if needed. They have expertise in vendor relations and resource management. Training Resources: Available for onboarding and educating the Stefano family members on operating their digital store. This ensures the Stefano family is equipped with the necessary knowledge and skills. Yosemite's Small Business Program Manager (Lou): Provides oversight and support for the project and offers guidance and assistance throughout the project lifecycle. Budget Allocation: $15,000 is allocated to the project this ensures financial resources are available for necessary expenses and contingencies.

## Slide 10: Cost-Benefit Analysis
Write out the formula for the cost-benefit analysis
To calculate the present value of the future benefit using the formula Future Benefit / (1 + discount rate)^n, I first need to determine the value of 'n' in terms of the number of years. PV of expected future benefit = Future Benefit / (1 + discount rate) ^n = $,36,000 / 1.20 = $30,000 PV of project cost = Cost / (1 + discount rate) ^n = $15,000 (as this value £15,000 is provided already)
Show the steps to get the cost-benefit ratio
Cost-benefit ratio = PV of expected benefit / PV of project cost Cost-benefit ratio = $30,000 / $15,000 Cost-benefit ratio = 2.00
State whether the investment is positive or negative
Cost-benefit Ratio = 2.00 Therefore it is a positive investment

## Slide 11: Timing and Methodology
What are the minimum and the maximum number of weeks required to complete the project?
For the minimum number of weeks, I would consider the longest individual task duration, which is building the storefront, social media integration, and recommendation engine, each taking 2 weeks. Therefore, the minimum number of weeks required would be 2 weeks x 3 features = 6 weeks. However, since there are dependencies such as onboarding and training Stefano's, creating social media channels, and creating a custom sales report, we add the longest of these dependencies, which is 1 week. So, the minimum number of weeks required to complete all tasks is 6 weeks + 1 week = 7 weeks. The maximum is from the assumption that each task starts only after the previous one is completed, therefore the maximum is 10 weeks. Building storefront, social media integration, and recommendation engine (Engineering): Each feature takes 2 weeks. Total for all three features: 2 weeks x 3 = 6 weeks. Inputting inventory data (Vendor): Takes 1 week. Onboarding and training Stefano's (Vendor): Takes 1 week. Creating social media channels (Marketing): Takes 1 week. Creating custom sales report (Vendor): Takes 1 week. Adding up all the durations: 6 weeks (for building features) + 1 week (inventory data) + 1 week (onboarding/training) + 1 week (social media channels) + 1 week (custom sales report) = 10 weeks.

## Slide 12: Timing and Methodology
What methodology do you propose to use for organizing the project: Waterfall or Agile? Explain your answer in 2-3 sentences.
I propose using the Agile methodology to organise the project of integrating The Stefano Shop into Yosemite. Agile offers flexibility, allowing teams to adapt to changes and deliver incremental value throughout the project. Given the diverse team members, varying levels of familiarity with technology, and the need for continuous collaboration and feedback, Agile would enable effective communication, quick iterations, and the ability to address evolving requirements efficiently. With stakeholders like Papa Stefano, who is wary of budget constraints, Mama Stefano, concerned about timely preparations for holiday shoppers, and Junior Stefano, eager to leverage technology. Using the agile's iterative approach ensures their active involvement and accommodates their evolving needs.
Based on your chosen methodology, list the meetings you need to schedule.
Project Kickoff Meeting: Gather all stakeholders, including the Stefano family, project team members, and relevant Yosemite representatives, to discuss project objectives, scope, roles, and responsibilities. Sprint Planning Meetings: Conduct regular sprint planning sessions with the project team (Aliyah, Moe, and Taylor) to define the tasks for the upcoming sprint, estimate effort, and set sprint goals. Daily Stand-up Meetings: Hold brief daily stand-up meetings where team members share progress, discuss any impediments, and plan for the day. These meetings help in maintaining transparency, addressing issues promptly, and ensuring alignment toward the sprint goals. Sprint Review Meetings: At the end of each sprint, organise review meetings to demonstrate the completed work to stakeholders, including the Stefano family, and gather feedback for further refinement. Retrospective Meetings: After each sprint review, conduct retrospective meetings with the project team to reflect on what went well, identify areas for improvement, and discuss actionable steps to enhance team performance in subsequent sprints. Stakeholder Check-in Meetings: Schedule periodic check-in meetings with the Stefano family to provide updates on project progress, address concerns, and ensure alignment with their expectations. Progress Review Meetings: Hold regular progress review meetings with Yosemite representatives, such as Lou, to provide updates on the project's status, discuss any challenges faced, and seek necessary support or resources. I would use the progress report for this, as Papa Stefano is very concerned about budget so may want regular updates., Ad-hoc Meetings: Additionally, be prepared to schedule ad-hoc meetings as needed to address urgent issues, resolve conflicts, or make critical decisions that may impact the project's progress.

## Slide 13: Step Two: Identify Your Stakeholders and Team Digital Project Management

## Slide 14: Power-Influence Classifications
You need to classify each member of the Stefano family and Yosemite team by their power level and influence on the project. You are already provided with assumptions/risks for each person.
Take a look at the Cast of Characters in the classroom or the 6th and 7th slide to learn more about each person.
As you learned in the Setting up Your Project/Stakeholder's Power lesson, this chart has only a "High" or "Low" classification. Below is a reminder of what each term means.
Power Level: The level of authority and decision-making power that a person has over a project. You could ask: Can this person make decisions about the project?
Influence: A person's ability to influence decision-makers through their personality style, interpersonal skills, and relationship with those in authority. You could ask: Can this person influence a decision-maker?

## Slide 15: Power-Influence Classification Grid
Stakeholder | Power Level | Influence Level | Assumptions and Risks
Papa Stefano | High | High | Decides for the family Worries about the budget
Mama Stefano | Low | High | Influences the family decisions Concerned about timing
Junior Stefano | Low | Low | Helps out in the business Uses own account for the store
Aliyah (Engineering Manager) | High | High | Leads all development work Final decisions with engineering are hers
Moe (Vendor Manager) | Low | Low | Likes to upsell Helps out in promotions Only one of his many projects
Taylor (Marketing Manager) | Low | Low | Can delay the tasks Limited role for the project
Lou (Program Manager) | High | Low | Only high-level overview Can help when things go wrong
Me (Project Manager) | Low | High | Executes the project in a timely manner Follows the decision makers
As you learned in the Setting up Your Project/Stakeholder's Power lesson, this chart has only a "High" or "Low" classification.
HINT: Take a look at the Cast of Characters in the classroom or the 6th and 7th slide to learn more about each person.

## Slide 16: RACI Chart
You need to fill out a RACI chart for your team, as you learned in the Setting up Your Project/Evaluating Team's Competency lesson. In the case of this project, it is usually the same person who is Responsible are Accountable for a task, since managers are working with their teams who are not part of the project.
Responsible: Stakeholders who will be responsible for executing actual tasks.
Accountable: The stakeholder - usually a manager - who has the duty of approving whether a task is truly being completed; there can only be one accountable person per task.
Consult: Anyone who has valuable insight necessary to successfully execute a task; there can be more than one consult for each task.
Informed: A stakeholder who expects to receive information and updates about a particular task. Most stakeholders will fall into this category.

## Slide 17: RACI Chart Sample Solution
There are questions you can ask that help you figure out the RACI chart. Let's do that for the first task: Build storefront.
Responsible: Who in the team builds the storefront? Aliyah, as she is the engineering manager.
Accountable: Who can approve the finished storefront? Aliyah, since she is the one who knows the technical problems.
Consult: Who can provide valuable insight while building the storefront? Moe, as he is the vendor manager, and the storefront is for them.
Informed: Who needs to be kept informed about progress on this task? It can be all other people (Me, Lou, Taylor) as other tasks depend on this one.

## Slide 18: RACI Chart
Tasks | Me, Project Manager | Lou, Program Manager | Taylor, Marketing Manager | Moe, Vendor Manager | Aliyah, Engineering Manager
Build storefront | I | I | I | C | A/R
Input Inventory Data | I | I | I | A/R | C
Build social media integration | I | I | C | I | A/R
Train Stefano’s on platform | I | I | I | A/R | C
Create social media channels | I | I | A/R | I | C
Build recommendation engine | I | I | C | C | A/R
Create Custom Sales Report | I | I | I | A/R | C
Engage stakeholders | R | A | I | I | I
Take a look at the 5th slide: "Yosemite teams and tasks," for information. Each manager has a team that works with them; therefore, they are Accountable AND Responsible for the work they do. Unlike them, you have a boss who needs to approve of your work.

## Slide 19: Step Three: Create a Project Plan Digital Project Management

## Slide 20: Create a Project Plan
In this step, you will reference the project scope, stakeholder analysis, and RACI chart to create a project plan for the proposed methodology.
Build a model of your plan for managing the Yosemite project. It should be a snapshot of the planning phase of the project. You can use the dates in your current year when creating the project plan.
Display this model in one of the two frameworks,
A Gantt chart for Waterfall OR
a Scrum board for Agile.
After you pick one model, be sure to include the information outlined in your project scope, stakeholder analysis, and RACI chart.

## Slide 21: Instructions based on your method
Waterfall Project Plan
You need to create a Gantt chart
Implement everything from the Project Plan Details on slide 21
Follow the instructions on slide 22
Skip slides 23-25, go to slide 26 and continue the project.
Agile Project Plan
You need to create a Trello board
Implement everything from the Project Plan Details on slide 21
Skip slide 22
Follow the instructions on slide 23-25

## Slide 22: Project Plan Details
In the project plan you should include at least the following tasks:
All tasks from the RACI Chart
At least 3 Status Reports - where you think it is appropriate
Follow the additional instructions for your plan depending on your method
You can assume the status reports take one day, and the documentation tasks 1-3 days.
Pay attention to:
It is a snapshot of the planning phase of the project
You can only assign tasks to Yosemite employees
The date of the tasks must correlate with the project plan
All tasks must have a start date and due date
All tasks must be assigned to the relevant person

## Slide 23: Additional Instructions for the Waterfall Project Plan
If you choose a Waterfall project plan in Step 2, you should include additional tasks related to stakeholder engagement, team management, and closure activities.
You have to include at least the following additional tasks:
A kickoff meeting
Closure meeting
Create a Gantt chart for your project by filling in the Gantt Chart Template provided in the classroom. Export or save the spreadsheet as a .xls or .xlsx file. Add this spreadsheet to your project submission folder.

## Slide 24: Additional Instructions for the Agile Project Plan
If you choose an Agile project plan in Step 2, you should organize the columns using Scrum phases:
Sprint Planning
Backlog
Work In Progress
QA
Release
Sprint Review
Include relevant tasks that occur in the initial and end phases of a Sprint. You have to include at least the following additional tasks:
Sprint planning task for each sprint
Sprint review task for each sprint

## Slide 25: Additional Instructions for the Agile Project Plan - Trello
Pay attention to:
The columns are based on Scrum phases
Include relevant tasks to initial and end phases of a Sprint
Label the cards according to the Sprint they belong to (e.g. Sprint 1, Sprint 2…)
Don’t forget to add dates to each card
Add assignees to each task
Trello Card Example

## Slide 26: Additional Instructions for the Agile Project Plan
Create a new Scrum board on Trello and make it public.
To make your board public, click on the Change Visibility icon and select Public > “Yes, make board public”
Copy the URL from your browser - it is the same as you are viewing the board with
https://trello.com/b/cwuLMWzH/stefano-shop-digital-store
To test your link, paste your link into an incognito browser window and open it. If it opens your board directly, your link is good.

## Slide 27: Step Four: Risk and Response Digital Project Management

## Slide 28: Risk Response Strategies
Here are the six types of response strategies you can choose from:
Avoid relates to adjusting plans so it prevents the risk from ever happening to or having an impact on your project. This strategy essentially makes the risk irrelevant to your project.
Transfer is the act of moving the risk to a different recipient by adding into the project plan a way to direct the risk in a certain direction.
Mitigate relates to proactively adjusting plans or acquiring new resources to lessen the potential consequences as much as possible or preparing for the impact of the risk.
Accept involves passively acknowledging that it will happen, or creating thresholds that trigger actions when the risk causes a certain type or level of problem.
Escalate is the act of presenting the risk to someone with the right authority or skillset to properly respond. In this case, the digital project manager cannot sufficiently do so.
Exploit involves creating an opportunity or solution out of a risk to take advantage of a problem's impact.

## Slide 29: Risk Scenario 1
The Stefano Shop project relies on the customer providing Yosemite with information on all products in its inventory. The Stefanos did not deliver the inventory list by the day you planned to put inventory data into the system. They promised to deliver the inventory information in a few more days.
Your task is to:
Analyze the above risk and describe how this affects the project. Address at least two different critical points of risk, like scope, cost, schedule, quality, stakeholder relationships, etc.
Choose a risk response strategy (see the valid strategies on the "Response Strategies" slide.)
Explain how you would apply the strategy in 3-5 sentences, including how it would impact the customer.
Fill out the Status Report for this scenario

## Slide 30: Risk Scenario 1 Response
How might this risk affect the project? | 
With Stefanos not delivering the inventory list by the day It was planned to put inventory data into the system, it could significantly impact the project in multiple critical areas. Firstly, it affects the project's schedule, potentially leading to delays in the development and deployment of key features such as the storefront, social media integration, and recommendation engine. These delays may cascade throughout the project timeline, risking the timely completion of the project within the scheduled 12 weeks which has been budgeted for. Secondly, there's a high risk to stakeholder relationships, particularly in terms of trust and collaboration. The delay may erode confidence in The Stefano Shop's commitment to the project, leading to strained relations between Yosemite and The Stefano family. This could hinder effective communication and decision-making/ It could also cause the schedule and quality concerns throughout the project lifecycle to worsen. | 
Selected risk response strategy: | Mitigate
Explain below how you would apply the strategy. | 
I would suggest to mitigate the risk. To do this I would ensure Yosemite allocates additional resources where possible or manpower to assist The Stefano Shop in compiling and delivering the inventory data on time. This may involve assigning temporary staff or providing technical support to improve the process. Yosemite would then demonstrate its commitment to supporting The Stefano Shop and ensure that the project stays to schedule within the 12 weeks. This would also mean the budget is more likely to be less impacted by delays. This strategy fosters a positive customer experience by minimising disruptions to the project timeline and maintaining confidence in Yosemite's ability to deliver on its promises. | 

## Slide 31: Status Report
You need to fill out the status report on the next page. It has to be based on Risk Scenario 1, which you can find in Slide 28. You also need to use details from the project scenario, which you can find in Slide 3.
The Status Report date is when the Vendor Manager was scheduled to begin the “Input Inventory Data” task in your project plan.

## Slide 32: Risk Scenario 1 - Status Report
Project Health Check |  | 
Scope | Status | Tasks: Completed/Pending
Time | At Risk | Completed: Technical Documentation completed for storefront StoreFront Development released Pending: Social Media Integration ongoing Marketing team started creating social media channels Recommendation Engine – not yet started More staff to be resourced to mitigate delays in receiving inventory list
Cost | At Risk | 
Quality | On Track | 
Project Highlights/Blockers
Highlights: The digital storefront for The Stefano Shop has been successfully designed, built, tested, and released on Yosemite's eCommerce platform. Social media channels have been created and integrated into the digital storefront, enhancing the shop's online presence and enabling direct communication with customers via various platforms. The recommendation engine has been developed and implemented, offering personalised product suggestions to customers to support increased sales. The Stefano family has undergone training and onboarding sessions. They also have documentation to support knowledge and skills. Blockers: This delay has already impacted the inputting of inventory data into the system, which could further add delays in other tasks, such as building the recommendation engine or creating custom sales reports. Without the necessary inventory information, the project team may struggle to progress with these tasks, leading to potential schedule delays and impacting the overall project timeline.
Project Summary
The project aims to digitise The Stefano Shop, a local business, by integrating into Yosemite's eCommerce platform, creating a digital storefront, social media integration, and a recommendation engine. Additionally, the project prioritises training the Stefano family to manage their digital store, which will modernise its operations and expand its customer outreach and interaction.
Digitalisalisation of Stefano Shop | Yosemite
Sarah Bulmer | 25th March 2024

## Slide 33: Risk Scenario 2
When the Engineering team began designing the recommendation engine, they informed you that the task was more complicated than anticipated. The Engineering Manager said it would take four weeks and cost an additional $3,500 to upgrade the AI service that powers the recommendation engine. That fee would have to be covered by the customer.
Your task is to:
Analyze the above risk and describe how this affects the project. Address at least two different critical points of risk, like scope, cost, schedule, quality, stakeholder relationships, etc.
Choose a risk response strategy (see the valid strategies on the "Response Strategies" slide.)
Explain how you would apply the strategy in 3-5 sentences, including how it would impact the customer.

## Slide 34: Risk Scenario 2 Response
How might this risk affect the project? | 
The identified risk regarding the recommendation engine being affects the project in several critical ways: Cost Impact: The additional four weeks and $3,500 cost overrun for upgrading the AI service directly impact the project's budget, exceeding the initial cost estimate. This could strain the budget allocated for the project and may lead to financial difficulties for The Stefano Shop. Schedule Impact: The extension of the recommendation engine development timeline by four weeks affects the overall project schedule. This delay could potentially cascade into other tasks and deadlines, impacting the timely delivery of the entire project, particularly if there are dependencies. It's too late to prevent the risk and the mitigation response won't be effective, the most appropriate risk response strategy in this scenario is to Accept the risk. The project team acknowledges the impact of the additional time and cost but chooses to proceed with the project despite these challenges. To apply this strategy, I would communicate the updated timeline and budget to The Stefano Shop, ensuring transparency about the situation and ensuring there is enough budget. With the increase in budget and schedule impacts the sponsor would need to approve the delay and additional costs. | 
Selected risk response strategy: | Accept
Explain below how you would apply the strategy. | 
To apply the "Accept" risk response strategy to the identified risk of the recommendation engine being more complex than anticipated, the project team would follow these steps: Acknowledge the Risk: Firstly, the team acknowledges the situation and recognises that the recommendation engine development will take longer than initially planned and will incur additional costs due to the need to upgrade the AI service. Communication: The project manager communicates the updated timeline and budget implications to all relevant stakeholders, especially to The Stefano Shop. It's crucial to ensure clear and transparent communication about the impact of the risk on the project's schedule and budget and gain approval. Adjust Project Plan: The project plan will need to be adjusted to accommodate the extended timeline and increased costs resulting from the risk. There also may be the need to adjust dependencies, milestones, and resource allocation to account for the delay. Cost Management: The Project Manager works with the Engineering Manager to ensure that the additional $3,500 cost for upgrading the AI service is accounted for within the project's budget. They may need to reallocate funds from other areas or seek approval for a budget increase if necessary. Timeline Management: The project manager works with the Engineering Manager to streamline any opportunities in the development process. Risk Monitoring: While accepting the risk, the team continues to monitor its impact throughout the project lifecycle. By accepting the risk and taking proactive steps to manage its consequences, the project team can navigate the challenges posed by the recommendation engine's complexity while still working towards achieving the project's objectives within the agreed-upon constraints. | 

## Slide 35: Step Five: Knowledge Documentation Digital Project Management

## Slide 36: Knowledge Documentation
Throughout the project and before its closure, you asked the team to create documentation for the company Yosemite and the customer. The documentation list is partially filled out; your task is to fill in the missing information. You can also add more documentation tasks to the list, as there are many more things that can be written down. To have a complete project plan, consider adding these tasks to your Gantt chart/Trello board.

## Slide 37: Knowledge Documentation
Task | Assignee | Place in Timeline | Reason for Documenting This Task
Storefront Technical Documentation | Aliyah | After finishing Build Storefront task | Documentation to support learning for Stefanos, and supports engineers for their further development.
Platform user’s manual | Aliyah | Before the training the Stefanos | A documentation that can be given to Stefanos as a manual
Recommendation Engine Documentation | Aliyah | Final Sprint near completion to ensure all stakeholders understand how the Recommendation Engine works. | A comprehensive guide for the end-users and maintenance teams
Lesson Learned Document | Project Manager | After the project is finished | A lessons learned log will provide insight into the remainder of the sprints for any lessons learned and support future projects to save time, cost or quality.
Status Report | Project Manager | Review and update at the end of each Stage (weekly) when required. Create In the Sprint Planning | Supports throughout the sprints to ensure key stake holders are updated on progress and ensure Backlog is on track. It can help to identify any issues or risks.
Communications Report | Project Manager | Review and update at the end of each Stage (weekly) when required. Create In the Sprint Planning | Supports throughout the sprints to ensure key stake holders are updated on progress, issues and risks.
Risks and Issues Log | Project Manager | Review and update at the end of each Stage (weekly) when required. Create In the Sprint Planning | Supports throughout the sprints to ensure key stake holders are updated issues and risks to add to the communications report.